# During the Event (Execution Phase)

This phase starts when the event status moves to Active.

## Objectives during the event

- Ensure smooth execution

- Resolve issues in real time

- Maintain visibility and control

- Capture evidence and data

- Avoid surprises for leadership

## A. Operational Monitoring (Real-time)

### What happens

- Monitor critical tasks (A/V, speakers, logistics)

- Identify blockers immediately

### System support

- “Live Event Dashboard”

  - Tasks in In Progress / Blocked

  - Overdue or near-deadline tasks

## B. Incident & Issue Management

### Typical issues

- Speaker delay or no-show

- A/V malfunction

- Catering shortfall

- Room change

- Security access issue

### Workflow approach

Create Incident Tasks during the event:

Incident Task Workflow

- Created → Assigned → In Progress → Resolved → Closed

### Best practice

- Incident tasks are linked to the event

- Mark them as Critical

- Auto-notify Lead + Owner

## C. Change Management (Controlled Adjustments)

### Examples

- Agenda time change

- Speaker replacement

- Session cancellation

- Room reassignment

### What the system should do

- Log the change

- Keep a change history

### Governance rule

- Only Lead or Owner can approve material changes

- System records:

  - Old value

  - New value

  - Who approved

  - Timestamp

## D. Evidence & Documentation Capture

### What to capture

- Photos (setup, sessions)

- Attendance sheets

- Speaker confirmation

- Signed documents

- Incident resolution notes

### Why this matters

- Audit readiness

- Dispute resolution

- Post-event reporting

- Compliance

# After the Event (Closure & Optimization Phase)

This phase begins when the event status moves to Completed.

## Objectives after the event

- Close open work cleanly

- Capture lessons learned

- Measure success

- Ensure compliance

## A. Event Closure Tasks (Mandatory)

Create a Post-Event Task Set automatically when event ends.

### Typical post-event tasks

- Post-Event Report

- Feedback Collection

- Incident Review

- Compliance & Audit Check

- Archival

### Workflow example

Draft → Assigned → In Progress → Waiting Approval → Completed

## B. Feedback & Evaluation

### What to collect (via survey)

- Attendee feedback

- Speaker feedback

- Internal team feedback

## C. Audit & Compliance Review

### What auditors look for

- Was the event approved properly?

- Were critical tasks completed?

- Who approved contracts?

- Were incidents handled correctly?

- Is evidence retained?

### System support

- Audit log

- Task history timeline

- Attachment records

- Approval trail

## D. Archival

### Archiving rules

- Event moved to Archived

- Read-only access

## E. Thank you emails

### Correspondence

- Send thank you emails to attendees

- Send participation certificates (if any) to attendees as well as speakers